## Slide 1: From Concept to Implementation: Are Our Projects Ready? National Regional Transportation Conference
July 17, 2025

## Slide 2: Session Agenda
Welcome – Carrie Kissel, NADO
Background Briefing - John Kaliski, Cambridge Systematics
Panel Discussion
  Gena McCullough, Bi-State Regional Commission
  Stuart Anderson, Iowa DOT
  Sam Parker, District Planner, Minnesota DOT District 7
  Carrie Kissel, NADO
Group Exercise
Next Steps

## Slide 3: Background
Initiated by the former TRB Committee on Strategic Management at 2025 TRB Annual Meeting
2 surveys conducted by AASHTO Committee on Planning; augmented by interviews conducted by Massachusetts DOT staff
Presented to AASHTO Council on Highways & Streets
Partnerships developed with AMPO, NADO
3
Notes: The American Association of State Highway and Transportation Officials (AASHTO) Committee on Planning and several state departments of transportation collaborated on a number of engagement activities over the last year to gather data on ways to enhance project delivery.
Two rounds of surveys were conducted as well as several interviews were held with DOT staff members. For the first survey, thirty-five DOTs responded and for the second twenty-eight submitted answers.
The intent of the first survey and the interviews were to better understand the data and stakeholder relationship needs to promote strong project delivery practices.
The second survey was specifically targeted to gain more information on the mechanics of delivering different types of projects.
These engagement efforts were conducted to help inform the upcoming reauthorization activities by AASHTO and the state DOTs for the federal funding legislation.

## Slide 4: AASHTO Survey Responses
Completed first survey only
Completed second survey only
Completed both first and second surveys

## Slide 5: Typical Timeframes for Pre-Construction
Chart: 
 | 0 | 0 | 0 | 7.1429 | 14.2857 | 42.8571
 | 7.1429 | 14.2857 | 28.5714 | 39.2857 | 35.7143 | 39.2857
 | 3.5714 | 39.2857 | 32.1429 | 25 | 35.7143 | 7.1429
 | 35.7143 | 25 | 17.8571 | 10.7143 | 3.5714 | 3.5714
 | 53.5714 | 21.4286 | 21.4286 | 17.8571 | 10.7143 | 7.1429
4%
36%
54%
New Road Construction
14%
39%
25%
21%
Bridge Replacement
14%
36%
36%
4%
11%
Traffic Safety Improvements
Maintenance on existing surface
7%
39%
7%
4%
7%
Bike/Pedestrian Infrastructure
7%
39%
25%
11%
18%
Roadway Reconstruction
29%
32%
18%
21%
43%
On average, please indicate the timeframes for pre-construction project development activities for the following project types in your state If your State DOT has a committee that approves projects to proceed with project development, please consider approval from that committee as the beginning of the pre-construction process.
Note: n = 28
2 - 3 years
3 - 4 years
1 - 2 years
More than 4 years
Less than 1 year

## Slide 6: Typical Environmental Permitting Process by Project Type
Chart: 
 | 18 | 7 | 3 | 0
 | 2 | 9 | 11 | 6
 | 1 | 1 | 9 | 17
  Less than 1 year
  1 - 2 years
  2 - 3 years
  More than 3 years
0
Note: n = 28
How often do permitting issues cause delays?
Chart: 
 | 0 | 14.2857 | 64.2857 | 17.8571 | 3.5714
Rarely
Sometimes
Never
Always
0.0%
Often
Categorical Exclusion (CE)
Environmental Assessment (EA)
Environmental Impact Statement (EIS)
On average, how long do the following environmental permitting processes take within your state across all project types?

## Slide 7: Key Challenges to Project Delivery
(1 = highest, 6 = lowest) | 1 | 2 | 3 | 4 | 5 | 6
Cost increases associated with materials | 34% | 14% | 14% | 9% | 17% | 11%
Utility provider/3rd party coordination | 6% | 37% | 20% | 14% | 23% | 0%
Environmental permitting | 14% | 23% | 26% | 20% | 17% | 0%
Acquiring rights-of-way | 23% | 17% | 11% | 40% | 3% | 6%
Coordination between levels of government | 14% | 9% | 20% | 17% | 37% | 3%
Other (please specify) | 9% | 0% | 9% | 0% | 3% | 80%
Chart: 
 | 34 | 6 | 23 | 14 | 14 | 9
 | 14 | 37 | 17 | 23 | 9 | 0
  Utility/3rd party coordination
  Acquiring ROWs
  Environmental permits
  Coordination between governments
  0%
  Other
  Materials cost increases
  43%
  40%
  37%
  23%
  9%
  48%
Ranking of challenges to project delivery
Top challenges ranked by responses
  1st choice
  2nd choice
1
2
3
4
5
6
Note: n = 35

## Slide 8: Key Challenges to Project Delivery
(1 = highest, 6 = lowest) | 1 | 2 | 3 | 4 | 5 | 6
Cost increases associated with materials | 34% | 14% | 14% | 9% | 17% | 11%
Utility provider/3rd party coordination | 6% | 37% | 20% | 14% | 23% | 0%
Environmental permitting | 14% | 23% | 26% | 20% | 17% | 0%
Acquiring rights-of-way | 23% | 17% | 11% | 40% | 3% | 6%
Coordination between levels of government | 14% | 9% | 20% | 17% | 37% | 3%
Other (please specify) | 9% | 0% | 9% | 0% | 3% | 80%
Ranking of challenges to project delivery
1
2
3
4
5
6
Note: n = 35
Open response comments
Railroads
Cost increases, non-material related
            Project development
            Personnel and contractor resources
Misaligned expectations
  e.g., local expectations vs state financial availability
Risk management
        e.g., not being ready for roadblocks

## Slide 9: Data and Metrics Variation
Chart: 
 | 69
 | 31
  No
  Yes
Does your DOT collect data in a way that allows for adequate tracking of project implementation?
Themes
Themes
Note: n = 33
Financial and budget tracking: Funding utilization, cost changes, long-term estimates to evaluate trends in material cost increases,
  “FDOT has a Program Management Office that tracks project costs and long-range estimates to evaluate trends in materials cost increases.”
Systems and processes: Embed tracking in dashboards and regular review
  “FDOT has a Production Monthly Performance Report dashboard that is reviewed every month with executive leadership.”
  “CDOT maintains an ‘Accountability Dashboard’ on the CDOT website to track the 10-year plan project status and funding.”
Schedule tracking: milestones, changes from scheduled dates, changes in letting dates, added/removed/moved jobs
Performance data: Roadway, bike/ped fatalities and serious injuries; Reliability of travel, congestion, and emissions reduction; pavement and bridge conditions
Integrated system: “A[n] integrated system for tracking project cost estimates, funding availability, design progress, project expenditures, as well as R/W, utilities, and construction progress all in one place...”
New tracking data: Completion time, on-time tracking, on-budget tracking,
New performance data: pavement treatment, sidewalk condition data
Predictive data: Future impact on use of motorized and non-motorized modes of transport

## Slide 10: AASHTO Core Policy Position-Project Delivery
Improve project delivery and program administration by increasing flexibility, simplifying environmental regulations, and reducing program burdens.

## Slide 11: How Are State DOTs Responding?
Improved data and analytics
Stronger partnerships with MPOs, RPOs, local governments
Earlier identification of potential risks; proactive coordination with resource agencies, utilities, railroads, other partners
Prioritizing funding with flexibility in mind
Electronic bidding and e-construction
Standardizing readiness criteria for key project types
Enhancing project agreements

## Slide 12: Panel Discussion
Gena McCullough, Bi-State Regional Commission
Sam Parker, District Planner, Minnesota DOT District 7
Iowa DOT rep (TBD)
Carrie Kissel, NADO

## Slide 13: Panel Discussion
What are some of the unique challenges to project readiness in rural areas?
What strategies have you successfully used to advance projects in rural areas?
What type of changes in policy, process, or data could help you more easily advance projects in rural areas moving forward?

## Slide 14: Group Exercise Instructions
Join a table
Review the background information
Discuss how you would define and assess project readiness
Assess some/all of the 8 projects in your handout – or share your own project
Identify key takeaways

## Slide 15: What’s Next: NCHRP Research
Completed
NCHRP Research Report 988, Rural Transportation Issues Research Roadmap
NCHRP 08-131, Access to Jobs, Economic Opportunities and Education in Rural Areas
NCHRP 08-147, Improving Public Transportation in Rural Areas and Tribal Communities
Underway
NCHRP Synthesis 20-05/Topic 56-11 , Practices for Transportation Planning in Non-Metropolitan Areas
NCHRP 08-179, Strategies and Actions for Collaboration: A Guide for DOTs, MPOs, and Partners

## Slide 16: What’s Next: Continued Collaboration and Action
AASHTO
AMPO
NADO
Others?